## Gantt Chart
ICT2201_P6-9: GANTT CHART
PROJECT TITLE |  | Air Manager
PROJECT MANAGER & MEMBERS |  | Gian Meng Rong Jon Tan Keefe Lee Wesley Chiau
COMPANY NAME |  | Airline Cabin Crew
DATE |  | 2022-09-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[7 empty] | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN | M | T | W | R | F | ST | SN
 | time axis 2022-09-01 to 2022-11-20
1 | Software Requirement Specification & Project Planning (Milestone 1)
1.1 | Generate Requirements List
1.1.1 | Admin & Manager Functional Requirements | Wesley | 2022-09-08 | 2022-09-09 | 1 | 100% | bar: 2022-09-08 to 2022-09-09
1.1.2 | Staff Functional Requirements | Meng Rong | 2022-09-08 | 2022-09-09 | 1 | 100% | bar: 2022-09-08 to 2022-09-09
1.1.3 | Non-Functional Requirements & Performance Requirements | Keefe | 2022-09-08 | 2022-09-09 | 1 | 100% | bar: 2022-09-08 to 2022-09-09
1.1.4 | Safety Requirements & Security Requirements | Jon | 2022-09-08 | 2022-09-09 | 1 | 100% | bar: 2022-09-08 to 2022-09-09
1.2 | Use Case Model | Jon | 2022-09-10 | 2022-09-14 | 4 | 100% | bar: 2022-09-10 to 2022-09-14
1.3 | User Interface Requirements | Wesley | 2022-09-10 | 2022-09-14 | 4 | 100% | bar: 2022-09-10 to 2022-09-14
1.4 | Requirements Specification Documentation
1.4.1 | Section 1: Introduction | Keefe | 2022-09-10 | 2022-09-12 | 2 | 100% | bar: 2022-09-10 to 2022-09-12
1.4.2 | Section 1.1: Product Scope | Keefe | 2022-09-12 | 2022-09-14 | 2 | 100% | bar: 2022-09-12 to 2022-09-14
1.4.3 | Section 1.2: Related Background Literature | Wesley | 2022-09-14 | 2022-09-16 | 2 | 100% | bar: 2022-09-14 to 2022-09-16
1.4.4 | Section 1.3: Intended Audience and Document Overview | Wesley | 2022-09-16 | 2022-09-18 | 2 | 100% | bar: 2022-09-16 to 2022-09-18
1.4.5 | Section 1.4: References and Acknowledgements | Wesley
1.4.6 | Section 2.1: Product Overview | Meng Rong | 2022-09-10 | 2022-09-12 | 2 | 100% | bar: 2022-09-10 to 2022-09-12
1.4.7 | Section 2.2: Product Functionality | Meng Rong | 2022-09-12 | 2022-09-14 | 2 | 100% | bar: 2022-09-12 to 2022-09-14
1.4.8 | Section 2.3: Assumptions and Dependencies | Meng Rong | 2022-09-14 | 2022-09-16 | 2 | 100% | bar: 2022-09-14 to 2022-09-16
1.4.9 | Section 3.5: Other Requirements
1.5 | Review Requirements and Use Case Diagram at Client Meeting | ALL | 2022-09-15 | 2022-09-15 | 1 | 100% | bar: 2022-09-15
1.6 | Document minutes of Client Meeting | Jon | 2022-09-15 | 2022-09-15 | 1 | 100% | bar: 2022-09-15
1.7 | Update Use Case Model | Jon | 2022-09-16 | 2022-09-18 | 2 | 100% | bar: 2022-09-16 to 2022-09-18
1.8 | Update User Interface Requirements | Wesley | 2022-09-16 | 2022-09-18 | 2 | 100% | bar: 2022-09-16 to 2022-09-18
1.9 | Details Use Cases 1 - xx | Jon | 2022-09-16 | 2022-09-19 | 3 | 100% | bar: 2022-09-16 to 2022-09-19
1.10 | Details Use Cases xx - xx | Keefe | 2022-09-16 | 2022-09-19 | 3 | 100% | bar: 2022-09-16 to 2022-09-19
1.11 | Software Estimation | Keefe | 2022-09-19 | 2022-09-22 | 3 | 50% | bar: 2022-09-19; 2022-09-22
1.12 | Project Management | Meng Rong | 2022-09-16 | 2022-09-19 | 3 | 100% | bar: 2022-09-16 to 2022-09-19
1.13 | Project Data Dictionary | Meng Rong | 2022-09-19 | 2022-09-21 | 2 | bar: 2022-09-19; 2022-09-21
1.14 | Individual Member Task Reflections | ALL | 2022-09-22 | 2022-09-23 | 1
1.15 | Review Peer Documentations | ALL | 2022-09-22 | 2022-09-23 | 1 | bar: 2022-09-23
1.16 | Correct and Finalise Report | ALL | 2022-09-22 | 2022-09-23 | 1 | bar: 2022-09-23
2 | Design Specifications & Management (Milestone 2)
2.1
2.2
2.3
2.4
3 | Test Plan and Prototype (Milestone 3)
3.1
3.2
3.2.1
3.2.2
3.3
3.3.1
4
4.1
4.2
4.3
4.4